## Stakeholders
SYNTHETIC DEMO — illustrative training case, not an authentic project record.
Stakeholder group | Primary interest | Influence | Engagement need | Synthetic status
Residents and tenant groups | continuity, affordability, safety | High | co-design workshops and plain-language updates | illustrative
Municipal urban development team | policy fit, delivery, public value | High | decision gates and statutory coordination | illustrative
Housing association | asset condition, finance, resident continuity | High | option appraisal and phasing agreement | illustrative
Transit operator | route safety and operational continuity | Medium | movement workshop and construction logistics | illustrative
Water authority | storage, discharge, flood resilience | High | technical pre-application review | illustrative
Local schools and community groups | safe routes and social infrastructure | Medium | term-time access planning | illustrative

## Engagement log
SYNTHETIC DEMO — illustrative training case, not an authentic project record.
Round | Timing | Question | Output | Status
01 | 2025-Q3 | What should be protected? | memory and continuity principles | complete — synthetic
02 | 2025-Q4 | Where do routes feel unsafe? | entrance and lighting map | complete — synthetic
03 | 2026-Q1 | Which public-space option is preferred? | rain garden and play-space priorities | planned — synthetic