## Programme
SYNTHETIC DEMO — illustrative training case, not an authentic project record.
Package | Indicative period | Scope | Dependency | Status
P0 Evidence | 2025-Q2 to Q3 | surveys, resident baseline, utilities | commissioners approval | synthetic complete
P1 Public realm pilot | 2026-Q1 to Q4 | rain garden, crossings, lighting | water authority and access plan | synthetic proposed
P2 Tower retrofit pilot | 2026-Q3 to 2027-Q4 | B-T02 envelope and entrance | structural intrusive survey | synthetic proposed
P3 Edge infill | 2027-Q2 to 2029-Q4 | new homes and community hub | planning and resident continuity | synthetic option

## Milestones
SYNTHETIC DEMO — illustrative training case, not an authentic project record.
Milestone | Gate question | Owner role | Evidence
Concept freeze | Is the spatial structure agreed? | design lead | spatial framework
Pre-application | Are statutory constraints understood? | planning lead | constraints register
Pilot tender | Is scope and risk priced? | commercial lead | cost plan and risk register