## Cost plan
SYNTHETIC DEMO — illustrative training case, not an authentic project record.
Work package | Quantity basis | Illustrative cost EUR | Confidence | Cost status
Public realm and rain gardens | 1.2 km connector | 4200000 | Class 4 / low | synthetic allowance
Tower B-T02 retrofit pilot | 116 homes | 6800000 | Class 4 / low | synthetic allowance
Community hub fit-out | 2400 m2 frontage | 3100000 | Class 5 / very low | synthetic allowance
New edge housing | 180 homes | 39600000 | Class 5 / very low | synthetic option
Resident continuity and temporary works | programme allowance | 2400000 | Class 5 / very low | synthetic allowance

## Assumptions
SYNTHETIC DEMO — illustrative training case, not an authentic project record.
Assumption | Impact if wrong | Action
No major soil contamination | excavation cost and programme increase | complete intrusive survey
Existing utility corridor can be diverted | blue-green spine alignment changes | commission utility scan
Funding supports mixed tenure | edge infill mix changes | test finance scenarios