## Risks
SYNTHETIC DEMO — illustrative training case, not an authentic project record.
Risk ID | Risk statement | Cause | Impact | Likelihood | Consequence | Mitigation | Owner
R-01 | Structural capacity limits retrofit | incomplete records | scope and cost increase | Medium | High | intrusive survey before pilot | structural lead
R-02 | Flood storage cannot discharge as assumed | water-authority constraint | landscape redesign | Medium | High | early hydraulic review | water lead
R-03 | Resident continuity plan is not funded | budget pressure | displacement and trust loss | Medium | Critical | ring-fenced allowance and governance gate | housing lead
R-04 | New edge creates noise exceedance | service-road activity | planning objection | Low | Medium | acoustic design and monitoring | environment lead

## Scoring guide
SYNTHETIC DEMO — illustrative training case, not an authentic project record.
Label | Definition
Critical | could stop or materially change the project
High | requires decision before next stage
Medium | manage through design development
Low | monitor through routine coordination